## UIA Project Plan
| Start Date | 2016-08-16
| Total effort | 232.7
Sr. No | Activity Description | Days | Start Date | End Date | % breakup | Dependency | Remarks
| UIA Project Plan |  | 2016-08-16 | 2016-12-26
| Requirement & Planning phase | 57 | 2016-08-19 | 2016-09-16
| Meetings with stakeholder to discuss functional and non-functional requirements | 8 | 2016-08-16 | 2016-09-01 |  |  | Scheduled for 12 days while effort is only 8 days
| Requirement Analysis & documentation | 7 | 2016-08-19 | 2016-09-06 |  |  | Scheduled for 12 days while effort is only 7 days
| Create Technical Architecture framework | 10 | 2016-08-24 | 2016-09-07 |  |  | Start 3 days after the requirement analysis & doc started
| Setup the development & testing environment | 5 | 2016-08-24 | 2016-08-31 |  |  | Start in parallel with framework building
| POCs, Setup for security & portal Integration | 10 | 2016-09-01 | 2016-09-15 |  |  | Start after environment is setup, depends on tasks 9
| UX design - Architecture | 5 | 2016-08-23 | 2016-09-06 |  |  | Start 2 days after the requirement analysis & doc started
| UX design - Wireframe | 5 | 2016-08-26 | 2016-09-06 |  | Completion depends on requirement documentation: Tasks 7
| UX design - Styling | 7 | 2016-09-07 | 2016-09-16
| Sign off - Requirement, UX design, Any template etc | 0 | 2016-09-16 | 2016-09-16 |  |  | It is milestone task
| Sprint 1- Scope definition & planning |  | 2016-08-19 | 2016-09-16 |  |  | Effort for this activity is estimated under requirement analysis
| Development |  | 2016-09-19 | 2016-11-30
| Sprint 1 - UIA Role & Few User role | 18.2 | 2016-09-19 | 2016-10-17
Design
| Design of activities in scope | 1.82 | 2016-09-19 | 2016-09-20 | 10%
| Document design | 0.91 | 2016-09-21 | 2016-09-21 | 5%
| Coding & unit testing | 9.1 | 2016-09-22 | 2016-10-05 | 50%
| UI development - | 10
| Services | 9
| Manage Question - create, update & delete | 4 | 2016-09-22 | 2016-09-28
| Retreive question list | 4 | 2016-09-28 | 2016-10-04
| Unit testing by developers | 1 | 2016-10-04 | 2016-10-05
Testing
| Functional testing by QA | 5.46 | 2016-10-06 | 2016-10-13 | 30%
Deployment & Release
| Deployment to integration server | 1 | 2016-10-14 | 2016-10-14 | 5%
| Sprint 2 -Scope definition & planning |  | 2016-09-19 | 2016-10-14
| Show & tell for built-in User Stories | 0 | 2016-10-17 | 2016-10-17
| Sprint 2 - Customer | 39 | 2016-10-17 | 2016-11-17
Design
| Design of activities in scope | 3.9 | 2016-10-17 | 2016-10-20 | 10%
| Document design | 1.95 | 2016-10-21 | 2016-10-24 | 5%
| Coding & unit testing | 19.5 | 2016-10-25 | 2016-11-07 | 50%
| UI development - | 14
| Services | 20
| Login service | 4 | 2016-10-25 | 2016-10-31
| Reset service | 4 | 2016-10-31 | 2016-11-04
| Retrieved saved quotes | 4 | 2016-10-25 | 2016-10-31
| Reterieve purchased policy | 3 | 2016-10-31 | 2016-11-03
| Update contact Information | 3 | 2016-11-03 | 2016-11-07
| Unit testing by developers | 2 | 2016-11-04 | 2016-11-07
Testing
| Functional testing by QA | 11.7 | 2016-11-08 | 2016-11-15 | 30%
Deployment & Release
| Deployment to integration server | 1.95 | 2016-11-16 | 2016-11-17 | 5%
| Sprint 3 -Scope definition & planning |  | 2016-10-17 | 2016-11-17
| Show & tell for built-in User Stories | 0 | 2016-11-18 | 2016-11-18
| Sprint 3 - Quote Engine & Renewal of Insurance | 97.5 | 2016-09-19 | 2016-11-30 |  |  | This sprint can run in parallel of Sprint 1 & 2
Design
| Design of activities in scope | 9.75 | 2016-09-19 | 2016-09-23 | 10%
| Document design | 4.875 | 2016-09-26 | 2016-09-30 | 5%
| Coding & unit testing | 48.75 | 2016-10-03 | 2016-11-04 | 50%
| UI development - | 21
| Services | 49
| Retreive quote | 6 | 2016-10-03 | 2016-10-11
| Update quote | 6 | 2016-10-12 | 2016-10-20
| Payment service | 6 | 2016-10-21 | 2016-10-31
| Update payment information -monthly | 6 | 2016-10-03 | 2016-10-11
| Update payment information -yearly | 6 | 2016-10-12 | 2016-10-20
| Retreive existing policy | 6 | 2016-10-21 | 2016-10-31
| Update policy | 5 | 2016-11-01 | 2016-11-04
| Unit testing by developers | 8 | 2016-10-25 | 2016-11-04
Testing
| Functional testing by QA | 29.25 | 2016-11-07 | 2016-11-25 | 30%
Deployment & Release
| Deployment to integration server | 4.875 | 2016-11-28 | 2016-11-30 | 5%
| Show & tell for built-in User Stories | 0 | 2016-11-28 | 2016-11-28
| Delivery | 21 | 2016-12-01 | 2016-12-26
| User Acceptance Testing | 15 | 2016-12-01 | 2016-12-22
| Rework if any & re-deploy code for UAT | 5 | 2016-12-01 | 2016-12-22
| Sign off- UAT | 0 | 2016-12-23 | 2016-12-23
| Production Install | 1 | 2016-12-26 | 2016-12-26
Warranty Support
Formulas:
Start Date = MIN([Start Date, row below]:E77)
Start Date = WORKDAY([Start Date, row above],3)
End Date = MAX([End Date, row below]:F77)
End Date = WORKDAY([Start Date],12)